# 3.12.08 Project Chart
The project chart implements the project-related charts. This includes the project overview chart, the work breakdown structure (project structure plan), target/actual comparison chart for projects and jobs, the milestone-trend-analysis chart, the visualization of degree of completion, time sheets and a skill matrix.
The following charts can be generated here:
- Project Overview Chart
- Project Structure Plan (Work Breakdown Structure)
- Project Chart Target/Actual
- Jobs Target/Actual
- Milestone-Trend-Analysis
- Degree of Completion Chart
- Skill-Matrix
## Project Overview Chart
This chart generates an overview of the most relevant key figures of the project. Here, the plan and actual time/effort and incurred costs/revenues are displayed as planned and actual values for the projects and sub-projects. Additionally in this chart, offer values and invoice values as well as degree of completion of projects and sub-projects are listed.
The planned costs specify the internal cost which are based on the planning data of the jobs and from the budget administration. The internal costs are determined from tracking and recording (TimeTracker) and cost recording. The project budget is, if necessary, defined in the project and the planned revenue is calculated from the external evaluation of the jobs and budget administration. The external revenue specifies all billable services in the system (time and costs).

## Project Structure Plan (Work Breakdown Structure)
The Work Breakdown Structure diagram illustrates the project structure. The work breakdown structure (project structure plan) in Projectile displays the relationship of the project and the sub-projects with the corresponding jobs. The logical structure of the project (project structure/project hierarchy) down to the jobs level is visualized graphically. This chart also contains important planned and actual data of the projects, sub-projects and jobs.

## Project Chart Target/Actual
The project chart target/actual provides an overview of the work services of the individual projects including the corresponding sub-projects. The target times and actual times for the project are displayed as a diagram and as a list. The planning data is determined directly through the assignment of the jobs to the project or sub-project and the actual times are used through tracking and recording in TimeTracker.
The chart also contains information for planned-start and planned-end, of the project status and the estimated degree of completion.
The chart can display the planned data and actual data graphically, if the option “with image” (format tab) is set.

## Jobs Target/Actual
The chart jobs target/actual provides an overview of the work services of the individual jobs of the selected projects. The planned times and actual times for the work packages are displayed as a diagram or as a list. The planning data is determined through jobs and the actual times are used through tracking and recording in TimeTracker.
The chart also contains information for planned-start and planned-end of the jobs, of the status (including the due date) of the jobs and the estimated degree of completion through TimeTracker.

The chart can display the planned data and actual data graphically, if the option “with image” (format tab) is set.
## Milestone-Trend-Analysis
The Milestone-Trend-Analysis (MTA) chart displays trends for completing the defined milestones. The milestone-trend-analysis is a future-related instrument used for controlling deadlines of a project: On regular reporting dates, the project scheduling is estimated through a query of trend data for the probable time of achieving the objective. Through the course of the curve, a trend can be concluded through the deadlines of the project. The due dates for the milestones can be administered in the document type deadline.
The course of the curve for this chart is interpreted as follows:
- an ascending curve means: a delayment => The milestone objective will be/is achieved late,
- a horizontal curve means: deadline is met => The milestone objective will be/is achieved on time and
- a descending curve means: the milestone objective will be/is achieved too early.

## Degree of Completion
The degree of completion chart displays a graphical overview of the previous estimates for the projects and jobs. These estimates can be performed in the projects and/or the sub-projects or in TimeTracker for the individual jobs. Further information can be found in chapter 4.2.7 Estimates.

## Skill-Matrix
The skill-matrix chart provides an overview of the project services for the selected projects and sub-projects regarding the individual occupations.